# 📌 PSL Dataset Expansion Plan (3 Days)

## 🎯 Goal

• Add 36 new videos per class (9 original + 27 augmented).
• Each member records 312 short videos (104 classes × 3 each).
• After augmentation, each class will have 96 videos total.

## 1. Technical Ground Rules (non-negotiable for consistency)

• Resolution: Record in 1280 × 720.
• Final Resolution: Crop to 1278 × 720 later with script (uniform dataset).
• Frame Rate: 30 FPS fixed.
• Duration: ~4 seconds (±1s is fine, but consistent per class).
• Visibility: Full upper body + clear hands visible in frame.
• File Naming:
   - Format: className_memberID_vidNumber.mp4
   - Example: hello_Zain_1.mp4, hello_Aarij_2.mp4
• Backgrounds/Lighting:
   - 3 different places per class (e.g., bedroom, living room, outdoor/porch).
   - Slightly varied lighting (natural/daylight, lamp, overhead light).
• Dress: Can remain same throughout; avoid busy patterns.
• Noise: Quiet environment preferred (audio will not be used, but avoids distractions).

## 2. Work Distribution (3 Members × 312 Vids Each)

• Each person covers all 104 classes with 3 videos per class.

• Sends it over Blip each night to team lead. (Folder Structure given below)
• Day Allocation (Fri–Sun):
   - Day 1 (Fri): Record 104 vids (1 per class). 
   - Day 2 (Sat): Record 104 vids (2nd per class, diff background).
   - Day 3 (Sun): Record 104 vids (3rd per class, diff background).

👉 By end of Day 3, each member has 312 videos (104 × 3).

## 3. Folder & Sync Structure

Shared repo/cloud folder structure:

PSL_Dataset/
   ├── member1/
   │     ├── class1/
   │     │     ├── vid1.mp4
   │     │     ├── vid2.mp4
   │     │     └── vid3.mp4
   │     └── class2/...
   ├── member2/
   ├── member3/
   └── script_folder/

## 4. Quality Control Checklist (Daily Routine)

Before uploading, each member checks:
✅ Resolution = 1280×720
✅ FPS = 30
✅ Hands visible, action clear
✅ Correct background variation (not same as yesterday’s)
✅ File named correctly
✅ Class folder correct

## 5. End of Weekend

• By Sunday night: Each member has 312 videos uploaded.
• By Monday: Run processing script (cropping to 1278x720). (By team lead)
• By Tuesday: Dataset ready with 96 videos per class.

## 🔑 Additional Suggestions

• Calibration Video: On Day 0 (Thursday night), each member records 2 test clips → share → confirm settings before committing.
• Progress Tracking: Simple shared Google Sheet with 104 rows (classes) × 3 columns (Fri/Sat/Sun). Mark ✅ after each recording session.